## August18
Agenda Item 4 d Risk Register
Risk No | Risk Description | Probablity | Impact | Overall Risk Rating | Owner | Consequence if risk is realised | Mitigation/action points | How will risk be reduced | Risk change since last report
1 | Lack of increase of the Council core grant undermine sustainable of HWH; role of HWH increasing with proposed legisation placing new Healthwatch responsiblities to report to, and engage with, with regional Integrated Care System. No funding increase for 2025 means significant funding restraints | High | Medium | 7 | HWH Board/ED | HWH would be forced to reduce capacity, and ability to deliver core grant activities and statutory fucntions and requirements, resulting in reputational damage (residents and other stakehlders) if HWH is unable to carry out its statutory responsilbities. | Managing future financial sustainability by reducing organisational spend. A sustainability action plan is in process | Significant savings have been achieved through the premises move, leaving St Leonard's relocating to Mainyard Studios. Further savings are being made through a restructure/reduction of back office/admin salary cost
2 | Current premises are not accessible nor are they public facing as based in St Leonard Hospital | High | Low | 0 | HWH Board/ED | Risk resolved through site move to accessible premises (move took place 16/01/2025) | Remove risk from risk register
3 | Contracts, pay and/or conditions of service for staff doesn’t meet the needs of the organisation | Low | Low | 0 | HWH Board | Risk resolved - Staff are being paid at the market average for their roles and salaries are fair. | Remove risk from risk register
4 | A lack of support or direction by Board members compromises governance and threatens delivery | Low | Medium | 7 | HWH Board | Perception that a director may be actively working against the best interests of the organisation . Risks may not be adequately reduced or mitigated resulting in Healthwatch not delivering statuory duties or contracted outcomes. Commissioners take action; an extreme case would be the termination of contracts. | Board agreed to watch this risk to ensure there is a sesnse of support for the organisation and staff team from ALL active board members. Action to be taken as required
5 | Poor external communications - the community isn't engaged with; potential partnerships are not working etc. | Medium | Medium | 7 | All | Inconsistent communication with external stakeholders has been flagged as a reputational risk | There has been an incident of communication with key stakeholders recently which was concerning for this risk - active board members are expected to adhere to the comms policy and this was not the case in this incident. | Reassurance has not been given around concerns about this isse. Appropriate action to be taken as necessary
6 | Risk identified payroll system is not cloudbased. The system currently sits on a desktop system held by the finance manager. Risk ashould the laptop be damaged that informatio will be lost, and risk that only finance manager has access | High | High | 9 | All | Risk should the laptop be damaged that informatio will be lost. Risk that only finance manager can access the system. | Payroll remains on on a single laptop. Recently finace manager was away from work and we were unable to access the system to run payroll | Finance laptop to be stored at the office and not to leave premises. Exec Director and Dep Director to be informed of all passwords to access finance functions
5 | THIS RISK WAS REMOVED IN 2021. WHILST IT IS NO LONGER CONSIDERED AN ACTIVE RISK IT IS WORTH HOLDING ON THE RISK REGISTER TO ALLOW THE BOARD TO CONSIDER WHETHER THEY ARE COMFORTABLE WITH THE LEVEL OF OVERSIGHT AND REPORTING AROUND FINANCES Financial procedures are no longer appropriate and not do ensure effective and appropriate Board oversight |  |  |  | HWH Board | Funds may be used inappropriately and/or misreported to Companies House/board do not have effective oversight | Accounting Standards to be reviewed periodically by Board trustees (not less than annually and led by the Treasurer) Appointment an external audit - Taub Forensic - reviewed finances in 2021 recommendations adopted by Board 29 September Meeting. | Good finacial reporting and governance now in place
Note 1 The following is a useful risk checklist against which activities/projects should be considered and risks identified
> The issue is likely to seriously prejudice or prevent achievement of a principal objective
> The issue is likely to result in a need to seek additional funding to allow it to be resolved or result in significant diversion of resources from another aspect of the organisation
> The issue will lead to a material impact on the accounts
> The Treasurer has flagged it as an area for concern and/or significant and needs action
> The issue will attract significant public interest, or may seriously damage the reputation of the organisation
> The issue will result in a formal action being taken by an external body
Note 2 Overall risk factor is produced by assigning ratings for likelihood and impact of the risk occurring
Likelihood - High, medium, low
| Impact - High, Med, Low |  | Risk Factor Look-up Table
| Overall risk rating - Red, Amber, Green | IMPACT↓
|  | High | 6 | 8 | 9
|  | Medium | 4 | 5 | 7
|  | Low | 1 | 2 | 3
|  | PROBABILITY→ | Low | Medium | High
Note 3 All 'Red' and 'Amber' rated risks need to have mitigating actions. 'Green' risks just need to be monitored and reviewed
Risks removed from main report
| Security of data e.g. General Data Protection Regulations are breached; data is compromised or lost by an external attack. | Removed from Risk register as is being well managed day-to-day |  |  | JW | Personal data belonging to individuals (including staff and volunteers) may be shared or changed without their consent. Information Commissioner's Office (ICO) and individual owners of the personal data must be informed unless the breach is unlikely to result in a risk to rights and freedoms. Data is lost in an outage | Staff and volunteers to be trained adequately to ensure compliance of GDPR. IT infrastructure, systems and work processes of the organisation to be regularly reviewed and updated when necessary to ensure compliance. Invest in IT systems. NB City of London Corporation is the data controller under GDPR. | Darren Morgan, the independent consultant has signed contract to be HWH Data Controller as part of his contract to provide data services to HWH. Policy and procedure updated Nov 2019
| The safeguarding is not sufficiently robust | Removed from Risk register as organisational safeguarding processes are effective. |  |  | JW/CPP | DBS checks may not be in place for all appropriate workers leading to risk to vulnerable contacts. Lack of risk assessment may lead to increased risk of injury to workers or the public. Potential of being sued | Safeguarding policies, DBS checks and Risk Assessments to be reviewed annually by board. Executive Director to ensure they are agenda items at board meetings.
| Complaints Charter Delivery | Removed from Risk Register as being well managed and current being reivewed and extended to other groups. |  |  | JW/CPP | Reputational impact of slow production and opportuntity for Hackney people to have better understanding of local complaints processes undermined | Ensure Charter poster and booklet produced. Distribution plan developed. News article drafted and date for photo for promotion set for 24 April 2019 | Executive Director overisight working with Chair
| Pandemic not changing pace of move towards Integrated Care System development (& CCG regional merger); 1. potential shift to PPI run regionally rather than locally . | Removed from risk register no longer applicable |  |  | HWH Board/ ED | Signficant loss of income results in need for significant HWH restructure. Significantly limits HWH influence as reduces reach and ability to hear public voice. Not having a functioning Healthwatch possible breach of NHS Constitution amd the Health and Care Act 2012. | Seek clarfication from NEL CCG and ICS on commitment on local spend on PPI activities. Develop a business case on the effectiveness of local PPI funding crucial to achieving the ambitions of ICS and Hackney people. Seek public assurance from NEL CCG of continued commitment to high level of public involvement; important Healthwatch is able to be the body set up to implement patient involvement and an exemplar of good practice. Use draft NEL CCG pledges to explain why not funding Healthwatch undermines those commitments. | Maintain good relationship with CCG/ICS and demonstrate the importance of active pulbic involvement to effectively achieving ICS ambitions. Continue develop relations with NEL CCG working with other HW. In discussion with CCG for overall contract with fully cost recovery. Seek meeting with CCG Director of Finance
| Interim Chair currently in post until AGM on 21st September. | Removed from risk register as permanent Chair appointed |  |  | HWH Board | Any delay in either confirming interim Chair in post long term or recruiting a new Chair will impact on the leadership of HWH and ability of the organisation to pursue stratgic objectoves. | Interim Chair remains in post until replacement is recruited. | Interim Chair remains in post until replacement is recruited. Role of Chair advertised and networks used to recuit a successor.
| Covid impact on staff and project deliverables. | Removed from risk register - No longer applicable |  |  | HWH Board/ED/DD | Undermines staff well being leading to poor performance in contract deliverables; HWh. Seen as unable to delivery contract and undermines the organisational sustainability and ability to carry out Enter and View. | Weekly staff well-being check in at every Thursday Team meeting. Work with commissioners and staff if project deliverables being undermined to re-configure contract to ensure delivery. Information Exchange meeting developed to continue to get resident feeback on services | Act on themes identlfied in staff meeting. Keep commissioners informed of contract issues. Ensure staff raise early any contract issues
| Healthwatch Hackney Contracts not delivered effectively |  |  |  | HWH Board/ ED | HWH lose contracts. HWH reputation as voice of Hackney residents damaged. Need to restructure HWH. Risk of commissioner retendering core or other contract, loss of core contract makes HWH unsustainable. | Assess concerns of Commissioners and key external stakeholders. No current major issues around delivery of contracts | Restructure complete. HR consultant contract in place
| The development needs of staff, volunteers and board are not met |  |  |  | HWH Board ED/DD | Staff, volunteers and board underperform; feel underused. The organisation does not get the most out of its people. Staff/vol/trustee turnover rises | Annual appraisals for all carried out by Management for staff and Chairs for board members, where learning and development needs identified, all followed up with regular, structured 121's. Budget for training and development. | Skills audit/board development and staff support all in progress/place
| Executive Director (ED) new appointment: Gap in appointment in ED leads to lack of capcacity to be fully involved local and regional meeting. Acting ED Now mitigating capacity issues but lack of stability until permanent appointment is made |  |  |  | Board/DD | Acting ED now in post. Risk to contract if permanent ED not appointed by 1st August (LBH deadline for appointment). Risk to continuity, reputation and staff morale caused by possibility of another change of leadership | Acting ED continues positive work and stabilisation with Board. | Appoinment now made
5 | Financial procedures are no longer appropriate and not do ensure effective and appropriate Board oversight | Low | High |  | HWH Board | Funds may be used inappropriately and/or misreported to Companies House/board do not have effective oversight | Accounting Standards to be reviewed periodically by Board trustees (not less than annually and led by the Treasurer) Appointment an external audit - Taub Forensic - reviewed finances in 2021 recommendations adopted by Board 29 September Meeting. | Good finacial reporting and governance now in place
| Improvement Programme imposed by LBH. Targets around governance, staffing, decision making, policies, memorandum of articles. All targets to be achieved by Sept 23 or talks will begin to withdraw HWH contract | High | High | 9 | HWH Board | If all targets are not met within the agreed time scale LBH will move to terminate HWH contract. HWH Board has taken the decision to recruit externally for permanent Executive Director. Recruitment process will take time, resource and focus away from implementing improvement programme | If an external appointment is made a new Executive Director will be responsible for working with the Board to implement the improvement programme during their induction period - APPOINMENT NOW MADE | We are confident that, following the ratification of the decision making policy at the October Board meeting, we have taken the right steps to meet the improvement plan targets